WP6 Deliverable 6.3

Plan and descriptions of the 2nd year experiments and demonstrations

Sa4CPS

ITEA 4 22007

Status: Draft

••••••••••••••••••••••••••••••••••••••••••••••••••••••

Edited by Dilara Bayar (ACD)

Including contributions from:

Dilara Bayar (ACD)

Ali Kafalı (ACD)

M. Oğuz Taş (Inovasyon)

H. Burak Erözdemir (Inovasyon)

Miikka Salminen (Modirum Gespi)

Mika Mononen (Modirum Gespi)

Grégoire Moreau (ADLC)

Pedro Faria (ISEP)

Luis Gomes (ISEP)

Ibrahim Arif (ERARGE)

Lander Vanhaverbeke (Vintecc)

Annika Pylväläinen (Enerim)

Tuuli Lindroos (F-Secure)

Sini Olkanen (F-Secure)

Jiří Havlík (IMA)

Tomáš Bureš (CUNI)

Juhani Latvakoski (VTT)

TABLE OF CONTENTS

1	Introduction	5

2	Methodology & Roadmap	6

3	Targeted business impacts and key performance indicators of the use cases	6

3.1	Targeted business impacts of the use cases	7

3.2	Key performance indicators of the use cases	11

3.2.1	Shared KPI for all of the use cases	11

3.2.2	More detailed KPIs of each use are described in the following:	12

4	Descriptions of contributions of each UC’s into the 2nd year experiments and demonstrations	19

4.1	UC 1 - Connected & Autonomous lightweight logistics for in-factory/out-factory supply chain	19

4.1.1	Contribution to 2nd year demonstration 1	19

4.1.2	Discussion and estimation of the targeted KPI	19

4.2	UC 2 - People and machine position awareness in production or logistics area	19

4.2.1	Contribution to 2nd year demonstration x	19

4.2.2	Discussion and estimation of the targeted KPI	19

4.3	UC 3 - Map at the centre of situational awareness in addition to real time video	19

4.3.1	Contribution to 2nd year demonstration x	19

4.3.2	Discussion and estimation of the targeted KPI	19

4.4	UC 4 - Critical electricity distribution grid operation in energy communities	19

4.4.1	Contribution to 2nd year demonstration x	20

4.4.2	Discussion and estimation of the targeted KPI	20

4.5	UC 5 - Security and location awareness of persons	20

4.5.1	Contribution to 2nd year demonstration x	20

4.5.2	Discussion and estimation of the targeted KPI	20

4.6	UC 7 - Multirouting secure awareness system for hunting and outdoors	20

4.6.1	Contribution to 2nd year demonstration x	20

4.6.2	Discussion and estimation of the targeted KPI	20

4.7	UC 8 - Secure, trustworthy and reliable drone operation control system	20

4.7.1	Contribution to 2nd year demonstration x	20

4.7.2	Discussion and estimation of the targeted KPI	20

4.8	UC 9 - Situational awareness and secure management of digital twin assets	20

4.8.1	Contribution to 2nd year demonstration x	20

4.8.2	Discussion and estimation of the targeted KPI	20

4.9	Project story	20

4.9.1	Contribution to 2nd year demonstration x	20

4.9.2	Discussion and estimation of the targeted KPI	20

5	Description of the demonstrations to be shown in the 2nd year review	20

5.1	Demonstration 1 <add name>	21

5.2	Demonstration 2 <add name>	21

5.3	Demonstration 3 <add  name>	21

5.4	Demonstration n <add name>	21

6	Conclusions	21

7	References	21

TABLE OF FIGURES

Figure 1. Sa4CPS WP6 Methodology	6

Figure 2. UC5 concept	17

Figure 3. LoRa and LoRa WAN demonstration environment and components	24

Figure 4. “Operations control center” module as part of ADLC’s systems architecture	25

Figure 5. Situational awareness platform inputs & outputs	26

Figure 6. Project story – hybrid simulation-based experiment of the Sa4CPS concept operation in the port environment	30

List OF TABLES

Table 1. UC1 WP Contributions to the 1st Year Experiments & Demonstrations	7

Table 2. UC1 1st year Planned Experiment 1	8

Table 3. UC1 1st year Planned Experiment 2	8

Table 4. UC1 1st year Planned Experiment 3	9

Table 5. UC1 1st year Planned Demo 1	9

Table 6. UC1 1st year Planned Demo 2	10

Table 7. UC1 1st year Planned Demo 3	10

Table 8. UC1 1st year Planned Demo 4	10

Table 9. UC2 WP Contributions to the 1st Year Experiments & Demonstrations	11

Table 10. UC2 1st year Planned Experiment 1	12

Table 11. UC2 1st year Planned Demo 1	12

Table 12. UC3 WP Contributions to the 1st Year Experiments & Demonstrations	13

Table 13. UC3 1st year Planned Demo 1	14

Table 14. UC4 WP Contributions to the 1st Year Experiments & Demonstrations	15

Table 15. UC4 1st year Planned Experiment 1	15

Table 16. UC4 1st year Planned Experiment 2	16

Table 17. UC4 1st year Planned Demo 1	16

Table 18. UC5 WP Contributions to the 1st Year Experiments & Demonstrations	17

Table 19. UC5 1st year Planned Experiment 1	18

Table 20. UC5 1st year Planned Experiment 2	19

Table 21. UC5 1st year Planned Experiment 3	19

Table 22. UC5 1st year Planned Demo 1	20

Table 23. UC7 WP Contributions to the 1st Year Experiments & Demonstrations	21

Table 24. UC7 1st year Planned Experiment 1	22

Table 25. UC7 1st year Planned Experiment 2	23

Table 26. UC7 1st year Planned Demo 1	24

Table 27. UC8 WP Contributions to the 1st Year Experiments & Demonstrations	26

Table 28. UC8 1st year Planned Experiment 1	26

Table 29. UC8 1st year Planned Experiment 2	27

Table 30. UC8 1st year Planned Demo 1	27

Table 31. UC9 WP Contributions to the 1st Year Experiments & Demonstrations	29

Table 32. UC9 1st year Planned Demo 1	29

Table 33. Project story related contributions to the 1st Year Demonstration experiment.	30

Table 34. Project story related 1st year planned experiment.	30

Table 35. 1st year planned experimental demonstration	31

Table 36. 1st Year Experiment & Demo Summary	32

Abstract

This deliverable document, D6.1: Plan and descriptions of the 1st year experiments and demonstrations, presents the planning and technical descriptions of the first-year experiments and demonstrations carried out in the context of Sa4CPS. Derived from the use cases defined in WP1 and refined through the architectural and technical work packages (WP2–WP5), the described experiments and demonstrations aim to validate key aspects of the Sa4CPS concept, including real-time situational awareness, secure communications, and adaptive cybersecurity mechanisms.

Each use case (UC1-UC9) outlines its planned experimental setup and demonstration goals, supported by relevant technological components from earlier work packages. In addition, a project-level hybrid simulation -based experiment simulating the operation of the Sa4CPS concept in a port environment is also planned. These activities serve as the foundation for the continued experimental iterations and evaluation tasks in the upcoming phases (T6.2-T6.4) and provide critical insights for both technological validation and stakeholder engagement.

List of Abbreviations

| Abbreviation | Explanation |
| --- | --- |
| AI | Artificial Intelligence |
| API | Application Programming Interface |
| BVLOS | Beyond Visual Line of Sight |
| CIS | Customer Information System |
| CPS | Cyber-Physical System |
| DSO | Distribution System Operator |
| FTP | File Transfer Protocol |
| HMI | Human-Machine Interface |
| IoT | Internet of Things |
| LoRa | Long Range (wireless communication technology) |
| ML | Machine Learning |
| PHM | Prognostics and Health Management |
| REST API | Representational State Transfer Application Programming Interface |
| ToF | Time of Flight |
| UC | Use Case |
| WP | Work Package |
| XAI | Explainable Artificial Intelligence |

# Introduction

This document

).

# Methodology & Roadmap

Figure 15. The schedule of the Sa4CPS project.

| MS6 | Preliminary designs of the concept enablers | The technical has been designed | MS0 + 18m (may 2026) |
| --- | --- | --- | --- |
| MS7 | Experiments v2.0 - use cases | Year 2: targeted for UC demonstrations & designs Checkpoint of the KPIs status, main focus on use cases. | (MS0 + 24m) (sep 2026) |

<add here a figure explaining, the linkage between the WP, UC outputs with the demonstrators>

# Targeted business impacts and key performance indicators of the use cases

## Targeted business impacts of the use cases

xxx

1. Business impacts in logistics – UC1 connected & autonomous lightweight logistics

Short description: The purpose of a traceability system is to track where a product is and where it goes along the supply chain (SC). End-to-end supply chain traceability enables organizations in the supply chain network to respond to volatile demand. Automotive SC is a specialized production-distribution chain that includes a comprehensive combination of participants and processes. In recent years, new tools have been developed to improve SC transparency, visibility, and traceability. Traditional central server-client technical solutions cannot meet expectations in terms of data integrity, confidentiality, system flexibility and adaptability. Via applying Sa4CPS concept solutions the following targeted business impacts are focused: Increase of Direct sales of component solutions, direct selling as a whole system, system as a service sales, and consulting and systems engineering services.

Main contributors: ACD, Alpata, Erarge, Inovasyon, Otokar

Market / competitors:

According to the study carried by AlliedMarket Research  [19], the global automotive logistics market was valued at $241.7 billion in 2021, and is projected to reach $433.6 billion by 2031, growing at a CAGR of 6.1% from 2022 to 2031.

Planned results:

2. Business impacts of positioning in production or logistics area – UC2 people and machine position awareness

Short description: Rapidly changing production is reflected in an advanced interaction among humans and machines (HM). The systems will create living and dynamically changing organism composed of a new specialized sensor technologies supported by AI components. Project concept will be done through a design, development, and implementation an AI based sensor system for a monitoring of an interaction among humans and machines within production site. An early alert service for collision avoidance will be developed, data sets acquisition process for objects (HM) featuring will take place, and a novel situation aware digital twin services provided. The targeted business impacts related to variability and smoothness of the production process, efficiency improvements via position awareness services of all process components, improved human safety and cost savings.

Main contributors: IMA, Cuni

Market / competitors:

Considering the new company business strategy after acquisition of IMA by automotive enterprise, IMA will pursue an effort to exploit the project results within company products development. Exploitation focus will aim at specific industrial automation, objects monitoring and tracking and at utilization of project results within production ecosystems. New generation of subsystem components, tested on prototypes, will help IMA to have a system implementing new components for security and object monitoring at the production site. The competitiveness of IMA company will be increased.

Planned results:

3. Business impacts via application of advanced maps in various situations – UC4 Map at the centre of situational awareness

Short description: Dynamic and complex situations in public safety cases, such as e.g. firefighting, require informative representation of the situation to the end users. Therefore, advanced maps, including information related to real-time videos, sensors, and devices geolocated, are focused. The targed impact is to enhance first responders' safety and operational efficiency via improved situational awareness.

Main contributors: Modirum | Gespi, Natlink, Polar

Market / competitors:

The ITEA Sa4CPS provides Modirum | Gespi’s software systems an expansion of situational awareness from IoT-environments. From the program we gain a capability to integrate the information from IoT-devices to our C2-systems with high level of security. We also can improve our AI-capabilities through the information and provide better understanding of the situation to our critical infrastructure customers. The features and understanding of the IoT-environments open us new opportunities within different authorities and provides us new ways of using our systems in cross-domain environments with multiple authorities. The program will improve our competitiveness with the critical communications and situational awareness customers.

Planned results:

4. Business impacts in critical energy distribution – UC4 critical energy distribution grid operation

Short description: The aim is to develop novel solutions related to distributed AI, explainable Ai and digital twins, and apply them in making situational awareness smarter. In addition, federated learning models are applied for energy communities. Targeted business impact is related to arising efficiency and smartness of energy flexibility services and optimization of the usage of energy resources. In addition, aligning these technologies with modern web application paradigms enables the development of interoperable, stakeholder-oriented platforms that support more efficient energy flexibility services and optimized resource usage, thereby accelerating a robust and transparent green energy transition.

Main contributors: CEL, Digitalmente, Enerim, ISEP

Market / competitors:

The UC result is related to energy communities and all the related players, including consumers, prosumers, energy vehicle charging points, distribution system operators, and flexibility aggregators.  In Portugal, there is not much competition as the market is just emerging where IT services companies are adapting their solutions to energy communities and flexibility provision.

Planned results:

5. Business impacts of sensing security situation for people

Short description: The aim is to provide comprehensive and adaptive security solutions that safeguard users in various digital and physical environments. F-Secure advanced system is designed to ensure users digital safety through three key features. Situation-aware protection activates during critical moments, such as online banking sessions or when connecting to unsecured WiFi networks, providing heightened security during high-risk activities. Context-aware protection adapts to your changing protection needs, adjusting security measures based on your context, influenced by long-term system behaviour. Lastly, our guidance feature anticipates potential risks and offers proactive user guidance to navigate and mitigate these threats effectively.

Main contributors: F-Secure

Market / competitors: The global cybersecurity market is rapidly growing, driven by rising cyber threats and digital transformation. In 2024, global information security spending is projected to reach $184 billion. The European market is also expanding, with estimates between $60 billion and $75.4 billion, growing at a CAGR of 8.5% to 12.3% through 2030.

Competitors: Bitdefender, Trend Micro, McAfee

Planned results:

6. Business impacts of multirouting secure awareness for hunting and outdoors

Short description: The energy efficiency, security, safety and interoperability of data sharing are focused. The aim is to bring connectivity and awareness into area where is bad mobile phone coverage or no coverage at all, by utilizing different radio technologies, devices and utilizing devices of other brands.

Main contributors: Natlink, Polar

Market / competitors:

38 M€ in 5 years. Starting from 4 M€ and ending to 12 M€

According to the customer surveys done Jan 2025 for Natlink’s customers, problems in mobile phone network coverage and data connection reliability are top 3 issues in all researched countries (Finland, Sweden, Norway, France). There are no real solutions for improving this. There are direct radios like Garmin, but not tools that are made for hunting groups and apps.  Research and solution created in the project, gives possibility to help much the problem.

For 50 years, Polar Electro has been manufacturing wearable devices for measuring heart rate in the B2C market segment. Over the past 10 years, competition in the B2C segments has intensified so much that Polar Electro's market share has gradually decreased to four percent. For this reason, Polar Electro will focus on B2B segments where the service business increases the productivity and profitability of human work. It is possible to monitor people's well-being, health and functional capacity in real time and 24/7 and optimize operations based on biometric data so that profitability and productivity can be improved. The advantages of Polar Electro are the versatility of wearable devices, scalability for different uses, and data services for real-time and post-processing of data and operational control. The Wellness, Health, Medical and Security segments have the above-mentioned based on the huge turnover potential just by considering care services for the elderly and the treatment of depression in working-age people in a pre- and post-clinical setting.

Planned results:

7. Business impacts of secure, trustworthy and reliable drone operations

Short description: The development of a secure, trustworthy, resilient, and reliable operation control system for drones that keeps humans, infrastructure, and the physical autonomous systems safe. This enables the switch from drone operations within visual line of sight of a pilot to the remote control of a large fleet of autonomous drones through automated systems and a small team of operators, leading to the profitable use of drones in civil drone operations. This is in line with the vision of the European Aviation Safety Agency (that creates rules for drone operations in the EU), and could lead to the creation of standards in the future. The targeted business impact arise from the development of a highly secure and reliable drone operations control system will lead to a fast scale-up of ADLC’s transportation service, and could make it a leader in the drone transportation industry. Further, it could reduce the costs linked to ADLC’s operations, improving its profitability, and enabling the access to more complex situations for its service.

Main contributors: ADLC

Market / competitors:

The drone logistics market is still nascent and there are very few companies worldwide offering daily delivery services using drones. Most companies operating in this area are currently focused on B2C last mile delivery (i.e. Delivering e-commerce small packages or meals to the homes of private individuals). Such companies, which include Wing (owned by Alphabet/Google), Manna Drone Delivery, Zipline,… are typically building an hyper-optimized solution for their specific use case and the suburban environments on which they are focused, from the airframe, to the loading mechanism, to the control system. In contrast, ADLC is aiming to delivering transport services in various complex environments (offshore, petrochemical ports,…) for industrial use cases. As a result, it will tend to use a much larger variety of drone systems, and fly in many different environments leading to the need for a centralised platform presenting information in a similar way no matter the location or drone system. In this market segment, a few companies are slowly emerging, and ADLC could consider licensing out the developed operations control software to them in the future. As a result, ADLC expects to grow to a team of more than 10 FTEs in 2027, with a revenue forecast of 10 M€.

Planned results:

8. Business impacts of secure-situational awareness and trustworthy management of cyber physical assets

Short description: The plan is to focus to R&D of a secure parameter and software update mechanism that keeps humans, infrastructure, and the connected autonomous systems safe. In automobile industry, over the air software updates are common. Take Tesla as an example. Industry is more cautious as a complete factory/production can depend on the stability of a machine. Our solution connects machines to a central cloud platform. Having the ability to change parameters and update software of smart assets (smart production lines, smart co-working systems, vision systems and robots) in a safe and secure way will allow production companies, machine builders and integrators to operate their machines in a more optimal way.

Main contributors: Vintecc

Market / competitors:

The European market for industrial remote monitoring and control reached €6 billion in 2024 and is projected to grow to €9 billion by 2030. This growth is further accelerated by heightened concerns around cybersecurity, fuelled by the unstable geopolitical landscape, mandatory compliance requirements (such as NIS2), and a growing market demand for certifications like ISO 27001. Consequently, industrial organizations are increasingly prioritizing cybersecurity investments, with situation awareness and secure remote update capabilities playing a critical role in mitigating risks and ensuring operational resilience. Vintecc partners with 9altitudes and Squadron to deploy Capture with the situational aware capabilities all over Europe.

Planned results:

## Key performance indicators of the use cases

yyy

### Shared KPI for all of the use cases

| Name of the KPI: Sa4CPS UC KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| - Autonomous lightweight logistics (UC1) | 0 | 5 | 1 |
| - People and machine position awareness in production or logistics chain (UC 2) | 0 | 5 | 1 |
| - application of advanced maps in public safety (UC 3) | 0 | 5 | 1 |
| - critical energy distribution (UC 4) | 0 | 5 | 1 |
| - sensing security of people (UC 5) | 0 | 5 | 1 |
| - multirouting secure awareness system for hunting and outdoors (UC 7) | 0 | 5 | 1 |
| - Secure, trustworthy, and reliable drone operation control system (UC 8) | 0 | 5 | 1 |
| - secure management of cyber physical asset (UC 9) | 0 | 5 | 1 |

Metric description of the Sa4CPS UC KPI

- Use case have been described (level 0)

- At least one technology demonstration related to the use case have been showed (level 1)

- Combined (at least two partners onboard) Use case demonstration showed (level 2)

- Sa4CPS concept related innovative identified contribution showed as the part of the combined use case demonstration (level 3)

- Cross-partner situational awareness operation with innovative identified contributions for Sa4CPS concept demonstrated (level 4)

  - latency estimation (L = high, medium, low)

  - reliability estimation (R = high, medium, low)

  - security/trust level estimation (T = high, medium, low)

- Sa4CPS story related secure situational awareness demonstration showed (level 5)

  - latency estimation (L = high, medium, low)

  - reliability estimation (R = high, medium, low)

  - security/trust level estimation (T = high, medium, low)

### More detailed KPIs of each use are described in the following:

- KPI autonomous lightweight logistics (UC 1)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Technology readiness level | TRL level 3 | TRL level 5-6 | TRL level 3 |
| The sensor system characterizes and monitors at least 4 types of object interactions | 0 | 4 | 1 |
| At least 2 services to prevent collision | 0 | 2 | 1 |
| Collecting data sets for 10 different object interaction features | 2 | 10 | 3 |
| Situation awareness model (semantic model) | 0 | 1 | 0 |
| Contribution to academic literature | 0 | 3 | 0 |
| Commercializable product | 0 | 3 | 0 |
| Number of services that will run on the final platform (x-as-a-service) | 0 | 9 | 0 |
| Field experimentation, demonstration and realization | 0 | 2 | 1 |
| Supporting at least 4 different communication protocols (BLU, RF, OpenTreath) | 0 | 3 | 2 |

- KPI People and machine position awareness in production or logistics chain (UC 2)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Human-machine anti-collision service | 0 | 2 | 1 Initial experiments performed processing 3D data of ToF camera projected in collored 2D visualization app in order to set anticollision algorithm |
| Robot assistance service | 0 | 2 | 0 |
| Contribution to academic literature | 0 | 1 | 1 Paper in www.scitepress.org Interpreting Workflow Architectures by LLMs |
| Lab experimentation, demonstration and realization | 0 | 3 | 1 Experiments with object/hand movement detection done. |
| Number of services w.r.t. SA4CPS final platform | 0 | 2 | 0 |

- KPI application of advanced maps in public safety (UC 3)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| AI solution (number of AI application areas, e.g. image recognition) | 3 application areas | 4 application areas | 3 application areas |
| Task planning solution (number of task planning support features) | 1 task planning features | 3 task planning features | 1 task planning features |
| Data anomaly alerting solution (number of alert types supported) | 0 alert types | 3 alert types | 3 alert types |

- KPI critical energy distribution (UC 4)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Number of consumers enrolled in flexibility program | 0 | 10 | 0 |
| Amount of Energy transacted (kWh) | 0 | 20 | 0 |
| Voltage issue events number | 20 | 2 | 20 |
| Average duration of voltage issues (min) | 30 | 10 | 30 |
| Average time required to solve voltage issues (min) | N/A | 10 | N/A |
| Line capacity issue events number | 45 | 5 | 45 |
| Average duration of line capacity issues (min) | 45 | 10 | 45 |
| Average time required to solve line capacity issues | N/A | 10 | N/A |

- KPI sensing security of people (UC 5)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| NPS (overall measure of experience) | 49 | 70 (by the end of the project) | 54 |
| CES (Customer effort score) | 82% | “use is easy” +90% | 83% |
| Sense of Security (feel safe using the product) | 86% | 95% | 86% |
| Trust (trust in F-Secure) | 90% | 95% | 91% |

- KPI multirouting secure awareness system for hunting and outdoors (UC 7) AP (Natlink, Polar): update current value & add clarification as footnotes

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Radio technology suitability tests (nr of Radio) Technologies: Bluetooth technology(ies), CAT M1, CAT 1 bis, LoRa 500mW and 25mW, Dect NR+, WiFi | 1 | 7 | 6 |
| Working prototype for Multicommunicator device, each of step can also have decimals, so if there are several rounds the final version gives full step. (1: components, 2: schematics, 3: PCB, 4: Mechanics, 5:FW, 6.Antennas, 7. Field test) | 0 | 7 | 5 |
| Working (prototype) devices to communicate with Multicommunicator device, via different radios | 0 | 3 | 3 |
| New communication protocols implemented and tested, 1: basic design, 2:ciphering ready, 3:IoT and RF designed, 4:IP data Routing, 5:mesh | 0 | 5 | 3 |
| DigitalTwins (2pcs), management, statistic, client uI, history, mapping systems implemented to support them | 0 | 7 | 2 |
| Security levels implemented: (Basic encryption for all interfaces (1-3), System is handling data viewing rights / ownership changes online, without losing history from original owner (4). System is handling data viewing rights / ownership changes even there is no Internet connection (5) | 0 | 5 | 3 |
| Service usage / maturity level (1=independent devices and point to point, 2=data forwarded to next device / server, 3 = data used as system, 4 = system used in other Sa4CPS party / demo, 5 = data / system used by externals / commercial ready status) | 0 | 5 | 2 |

Situational awareness system for personal and group guidance (UC7, Polar)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Creating groups, managing members, defining permissions and user roles. Invitations to members through groups, creation of coaching and guidance relationships, and drafting agreements Defining users, setting goals, choosing content and plans | 0 | 1 | 1 |
| Creating groups, managing members, defining permissions and user roles. Invitations to members through groups, creation of coaching and guidance relationships, and drafting agreements Defining users, setting goals, choosing content and plans | 0 | 1 | 1 |
| Goal setting and user profiling An annual planning "almanac" that includes periods, months, weeks, and events The almanac sets limits for quantities and qualities in the content production phase (summary = plan) There are data classification rules for plans and time periods for mass customization In mass customization, members, groups and content are combined into guidance frameworks that meet the goals Frameworks can be saved for reuse | 0 | 1 | 1 |
| Real-time monitoring (load, recovery, levels, accumulation, reference scales) Summaries: reports of individual exercises, long-term trends (numerical, graphical), target view | 0 | 1 | 1 |

1 = Requirements spesifications and preliminary UI models are created

2 = Architectural structure is defined ...

- KPI Secure, trustworthy, and reliable drone operation control system (UC 8)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Deliveries per day per pilot - this amount should increase since labour tasks are reduced, and the increased situational awareness allows for the potential monitoring of multiple concurrent flight operations by one pilot. | Currently, it is estimated that a pilot can handle 4 to 5 deliveries a day. | ADLC aims to reach a technical and operational capability of 25 deliveries per day per pilot. | Currently, it is estimated that a pilot can handle 4 to 5 deliveries a day. |
| # Incident per 100 flights - incidents are any unwanted occurrences that could have a negative impact on the safety of a flight operation. All incidents in our flight operations are recorded, so we will be able to precisely determine if there is an improvement. | Current estimation: around 10 per hundred flights | There is a high variability to such measures, and they depend on more factors than the quality of the developed situational awareness platform. However, the first measure has a direct impact on ADLC’s financial viability, and it will only be possible to increase it if it coincides with a decrease of the second. | Current estimation: around 10 per hundred flights |
| Time to respond to incidents. Generally, faster response prevent escalation | Up to 30 seconds | Less than 5 seconds | Up to 30 seconds |

- KPI : secure management of cyber physical asset (UC 9)

| Name of the KPI | Initial value | Targeted value | Current value |
| --- | --- | --- | --- |
| Update of the Capture server software and Capture edge and industrial device control software and parameters can be realized in a secured way. This means all measures are taken to ensure a safe state in which updates, validation and rollback is possible in case of detected problems. The validation of correct behaviour must be possible by comparing in real-time the physical behaviour to the simulated Digital Twin behaviour, while ensuring no physical harm can be done by unexpected actions. The measurable indicator is the demonstration of such update scenarios in Vintecc lab environment open to the critical remarks and investigation by the consortium partners. | Capture Edge and other edge software can be updated in a Linux and Windows environment, but not in a Docker environment. Validation and rollbacks are done manually. | We demonstrate we can update Capture Edge and other edge software in a container environment in a safe manner. | Windows, Linux support, partial support for Docker containers |
| Total trusted access control is realised on all levels (capture server, edge controller and industrial device) avoiding any unwanted intrusion. This will be verified by an expert subcontracting organisation using all her experience to try and access on each of the possible levels to take over control. This test should be 100% successful in terms of protection. | No expert subcontracting organisation has tested the security of remote updates. | The expert subcontracting organisation rapports that the remote updates done by Capture are secure. | No expert subcontracting organisation has tested the security of remote updates. |
| Based on the results of this project Vintecc will define a strategy to continuously maximise its software protection against new cyber security dangers threats to be able to ensure its customers on building and maintaining safe and reliable solutions. | We don’t have a general strategy to keep edge devices up to date and secure, these are done case by case. | We have a general strategy to keep edge devices up to date and secure. | Security issues have been identified. Work has started to handle these issues. |
| Vintecc will design and develop an architecture to embed these cyber security concepts as integrated part of its existing “capture” and “dual” framework. This should allow for automated update testing as well as safe state pre-update and post-update actions. | Edge updating is possible for Linux and Windows devices from the Capture cloud portal. This is not possible for container environments. We don’t have a mechanism that clearly indicates to the user when an update is required for security reasons. | A user can update Capture Edge on all environments from the Capture portal. It is easy for the user to detect required updates, trigger the update and validate the results. | An MVP of pre-update checks has been implemented and is currently being reviewed. |

# Descriptions of contributions of each UC’s into the 2nd year experiments and demonstrations

## UC 1 - Connected & Autonomous lightweight logistics for in-factory/out-factory supply chain

### Contribution to 2nd year demonstration 1

### Discussion and estimation of the targeted KPI

## UC 2 - People and machine position awareness in production or logistics area

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 3 - Map at the centre of situational awareness in addition to real time video

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 4 - Critical electricity distribution grid operation in energy communities

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 5 - Security and location awareness of persons

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 7 - Multirouting secure awareness system for hunting and outdoors

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 8 - Secure, trustworthy and reliable drone operation control system

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## UC 9 - Situational awareness and secure management of digital twin assets

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

## Project story

### Contribution to 2nd year demonstration x

### Discussion and estimation of the targeted KPI

# Description of the demonstrations to be shown in the 2nd year review

## Demonstration 1 <add name>

## Demonstration 2 <add name>

## Demonstration 3 <add name>

## Demonstration n <add name>

# Conclusions

This

.

Table 36. 1st Year Experiment & Demo Summary

| Use Case | Number of Experiments | Number of Demos | Focus Area |
| --- | --- | --- | --- |

The outcomes).

# References

- No references have been used in this document.

Alpata has reported that their parts are already in the TRL level 5, because dummy datasets used for software tests.

Alpata has reported 3 object interaction types (pallet, box, person).

HTTP and MQTT are supported.

Based on video feed: object detection & classification, object localization, automated alarms if ”object“ inside geofence area(s)

”Go and check the area.” - message if objects seen at unauthorized areas.

GPS coordinates on satellite image, Image data of an object, alert message how to react

Current value is based on F-Secure's user experience metrics in June 2025

BT tested, CAT M1 tested, CAT 1 bis partly tested, LoRa 500mW and 25mW tested, DectNR+ tested, WiFi studied.

0,5 Initial components selected, 0,5 Initial schematic done, 0,5 PCB layout design done, 0,5 ID design done, 1 Antenna study done

Basic design and ciphering design done

This value has not changed since the beginning of the project as the initial platform is not yet sufficiently mature to be used in-flight yet. It is expected that an initial version of the platform will start being used in operations in H1 2026.

Same as footnote above.

Same as footnote above

Windows and Linux environments can be updated using the Capture platform. Docker containers can be updated through the Balena platform.

ISO27001 certification is work in progress. We use the ISO requirements to identify security issues with Capture Edge.